## Slide 1
StrideAI — AI Adaptive Running Coach
Executive technical program case study
The opportunity
Make personalized, continuously adaptive coaching accessible to everyday runners from 5K to marathon.
Core differentiation
The smartest adaptive running coach — continuously adapting training from performance, recovery, wearable data and real-world conditions.
200K Downloads
>4.7/5 Rating
>50% 30-day retention
>70% Recommendation acceptance
StrideAI | Technical Program Management Portfolio 1

## Slide 2
Product & Technical Strategy
Prioritize the differentiator before secondary features
MVP priority
Wearable sync
Training load
Recovery / fatigue
Confidence-based adaptation
Safety rules
Recommendation explanation
Deferred to Phase 2
Race predictor
Weekly summaries
Advanced progress tracking
Decision architecture
Wearable + Workout Data
Data Processing
ML / Fatigue Model
Confidence + Adaptation
Deterministic Safety Rules
LLM Explanation
StrideAI | Technical Program Management Portfolio 2

## Slide 3
Six-Week Program Plan
Critical path: validated data → fatigue model → safe adaptation → launch
W1
Architecture API + schemas
W2
Data ingestion End-to-end slice
W3
Training load Recovery + fatigue
W4
Adaptation Safety + explanation
W5
Integration Performance + monitoring
W6
Internal beta Controlled rollout
Critical milestone
End of Week 2: one real workout flows end-to-end and produces a basic recommendation.
Program operating rhythm
Weekly program review • technical deep dive • dependency resolution • executive update
StrideAI | Technical Program Management Portfolio 3

## Slide 4
Key Technical Decision
Use AI where it adds value — keep safety-critical behavior predictable
Option A
LLM decides workout adaptation
Flexible and easy to evolve but harder to test and guarantee.
Option B — Recommended
ML + deterministic logic decide LLM explains the decision
More predictable, testable and auditable. Better fit for safety-critical coaching.
Decision flow
Signals
ML / Rules
Confidence
Safety
Workout
LLM explanation
Principle: the LLM explains the decision; it does not independently invent safety-critical adaptations.
StrideAI | Technical Program Management Portfolio 4

## Slide 5
Major Program Risk & Executive Trade-off
Recommendation quality is the critical path risk
Current 74%
Production target 80%
Why it matters
Adaptive coaching is the core competitive advantage. Low-quality recommendations directly threaten user trust and product differentiation.
Commercial pressure
Delaying the announced launch risks a major partnership.
Quality pressure
A 100% rollout below the quality bar risks damaging the core product proposition.
Recommendation
Internal → Beta → 20% → 40% → 100%
Expand only when quality, safety and reliability gates pass. Pause or roll back if critical thresholds fail.
StrideAI | Technical Program Management Portfolio 5

## Slide 6
AI Quality & Safety Framework
Do not reduce AI quality to one accuracy number
1. Model quality
Precision • Recall • F1 Calibration • error rates
2. Decision quality
Expert review Historical backtesting
3. Safety
Critical safety violations Target: 0
4. User outcomes
Acceptance • overrides Retention • satisfaction
Controlled rollout gates
Internal
Beta
20%
40%
100%
Each expansion requires evidence-based quality, safety and reliability gates. Rollback criteria are defined before launch.
StrideAI | Technical Program Management Portfolio 6

## Slide 7
Executive Recommendation & TPM Value
Turn technical uncertainty into measurable decisions
Recommendation
Protect the commercial launch through controlled exposure while protecting the quality bar through evidence-based gates.
What I would drive as TPM
• Align Product, Engineering, Data Science, QA and Platform on the critical path.
• Quantify trade-offs instead of escalating symptoms.
• Make AI quality, safety and rollout gates explicit.
• Track dependencies, owners, triggers and mitigation.
• Give executives a clear recommendation and decision request.
Portfolio outcome: a complete AI technical program case study — strategy, architecture, execution, risk, AI evaluation and launch governance.
StrideAI | Technical Program Management Portfolio 7